PROJECT PLAN DELIVARABLES

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Personnel | Shirwa | Ancila | Matt | All | When they were delivered |
| Week 13 | Code; Draft code for sending data to the central board  Document; Sensor server design | Document1; Test plan document for the sensor server | Document2; Monitor design |  | Code; week13  Document1; Week 13  Document; Week 13-21 |
| Week 14 | Code1; complete code for sending data to the central board  Code; Draft code for sending sensor values to the monitor | Document1; Test plan document for the monitor | Code2; Monitor code for moving the chair accordingly | Document2; Functional specification | Code1; Week 14  Code; Week 14  Document1; Week 23  Code2; Week 22  Document2; Week 14-20 |
| Week 15 | Code; A complete Sensor server code together with sending data to the monitor | Document; Test plan document for the whole system | Document; Monitor design |  | Code; Week 15  Document; Week 23  Document; not available |
| Week 16 | Testing the sensor server module |  | Code; A complete monitor code |  | Testing week 20  Code; Week 22 |
| Week 17 | Document; Functional specification | Document1; A draft write up of the report  Document; Recording the results for the testing | Testing the monitor module |  | Document; Week 14-20  Document1; Week 23  Testing; Week 22 |
| Week 18 |  |  |  | Testing the whole system | Week 24 |
| Week 19 |  |  |  | Documentation | Week13-24 |
| Week 20 |  |  |  | Finalizing everything | Week 25 |

Most of the tasks given to each person were delivered a little bit late because each person had a different way of working, starting with matts deliverables they were all delivered late since he was not available to work on his tasks and he would rarely show up for the workshops and at the end he was not able to continue this project with us and so we had a third party to carry out his tasks and so they were delayed.

The next will be the sensor server tasks, these tasks were done in time just a few updates were made to them each week and at one point we had to change a certain hardware that was being used and so some tasks were delayed.

Documentation was delayed because of certain reasons like we did not have the full idea of how the monitor was supposed to work and so the test plan for it was totally delayed. At the same time the functional specification and the sensor server design documents were done throughout the whole period since we kept modifying the system and so the documents kept being updated. The monitor design is yet to be done because the module itself was created by a third party and so will be delivered soon.